RESEARCH PROPOSAL ¦ 12-MONTH PILOT ¦ PEDIATRIC BRAIN TUMOR IMMUNOTHERAPY

# Test Before You Treat

A shippable immune-cell platform to personalize immunotherapy for childhood brain tumors

| UTAH · CELLS, FREEZING, SHIPPING Samuel H. Cheshier University of Utah · Huntsman Cancer Institute · Intermountain Primary Children’s Hospital | UNC · SLiCE TESTING Andrew B. Satterlee University of North Carolina at Chapel Hill · Eshelman School of Pharmacy | PROJECT PERIOD 12 months | REQUEST $75,000 $50,000 Utah · $25,000 UNC |
| --- | --- | --- | --- |

| 40–50% of children’s malignant brain tumors grow reliably in a mouse brain, today’s most rigorous test | 4 days for SLiCE to test a patient’s tumor on living brain tissue. Mouse studies take months. | 5 of 5 aggressive childhood brain-tumor types responded to anti-CD47 therapy in mouse studies | ~85% less tumor-cell invasion with NG2-targeted macrophages in a patient-derived glioma model |
| --- | --- | --- | --- |

THE BIG IDEA For a child with a malignant brain tumor, there is no time to guess. Immunotherapy, which recruits the body’s own immune cells to destroy cancer, is among our most promising new tools. Yet doctors have no practical way to learn, before treatment, whether a particular child’s tumor will respond. We have a four-day test, called SLiCE, that grows patient tumors on slices of living brain. What it lacks is immune cells that can travel. In 12 months, we will learn to freeze, ship and thaw macrophages, the immune system’s cleanup cells, so that hospitals can send a tumor to one central hub and receive an answer matched to that child.

# Why this matters

Malignant brain tumors cause more illness and death than any other childhood cancer.3 Many weave through healthy brain or sit where surgery is not possible. Radiation and chemotherapy can leave survivors with lifelong physical and intellectual disabilities and a higher risk of later cancers, and radiation often cannot be used in the youngest children. Children with the brainstem tumor DIPG usually live less than a year after diagnosis.3 Immunotherapy offers a smarter, gentler path, and macrophage-based treatments are already entering clinical trials. But early results have been mixed,5,6 and responses differ from tumor to tumor. Choosing the right immunotherapy for a child requires a test on that child’s own tumor.

The most rigorous preclinical test is to implant a patient’s tumor into a mouse brain and treat the mouse. This work has been invaluable, but it takes months, is expensive, and works for only 40–50% of malignant childhood brain tumors; the rest will not grow reliably. Worse, mice that can grow human tumors lack a fully working immune system, so they cannot show whether an immunotherapy will work. For the treatments we most want to test, the gold standard falls short, and precision medicine is nearly out of reach.

# What we already have

| 1 · A four-day test on living brain |  | 2 · Release the brake |  | 3 · Add a homing device |
| --- | --- | --- | --- | --- |
| Dr. Satterlee’s SLiCE platform (Screening Live Cancer Explants) places a patient’s tumor on a slice of living brain and tracks its response to treatment for four days, measuring both tumor killing and harm to normal brain tissue. In a first study of childhood low-grade glioma, tumor tissue survived 43 times better on brain slices than in a standard lab dish, and tumors differed in how they responded to drugs, as in real patients.1,2 SLiCE has also measured killing of tumor cells by immune T cells. |  | Macrophages are immune “eater” cells. Tumors wear a “don’t eat me” flag called CD47; an antibody that blocks it switches macrophages on. In mice, this reduced tumor burden and extended survival in all five aggressive childhood brain-tumor types tested, sparing normal human neural cells.3 In new work, macrophages from newborn cord blood ate more medulloblastoma cells than adult macrophages when the antibody was added, in all three cell lines tested.4 |  | We engineered macrophages with a synthetic receptor (a CAR) that locks onto NG2, a protein on many gliomas. In 3D lab models, they ate glioma cells, shrank glioblastoma mini-tumors by about 75% and blocked about 85% of invasion by patient-derived tumor cells, leaving NG2-low cells alone.5 The same approach against the same target (CSPG4) slowed melanoma growth in mice,6 and CAR macrophages were safe in early human trials in other cancers.5 |

The catch: these tools have mostly been tested in dishes and in mice without a working immune system, not on a child’s own tumor in SLiCE. And freshly made donor macrophages vary and cannot yet be frozen and shipped.

# The missing piece: immune cells that can travel

SLiCE is robust, but it is hard to recreate at every hospital. So we propose a hub-and-spoke network: partner hospitals send tumors to UNC, where experts run SLiCE, and receive results. Tumors are solved, because we already know how to preserve living tumor tissue for shipping. Immune cells are not: preserving viable macrophages for use in SLiCE has not yet been established. Until it is, an immunotherapy testing network cannot exist. This project solves it.

Figure 1. The network we are building. Frozen tumors can already travel to the hub; this project makes frozen macrophages travel-ready.

# Aims and approach

Both aims use pediatric hemispheric high-grade glioma (pHGG), a fast-growing tumor of the brain’s upper hemispheres, and follow the same two steps: find the best freezing recipe, then prove it works after a real shipment.

| AIM 1 · Normal macrophages: newborn cord blood vs. adult |  | AIM 2 · Engineered macrophages: NG2-targeted CAR |
| --- | --- | --- |
| Freeze, thaw and ship macrophages without losing their appetite for tumor. 1.1 Find the best freezing recipe. We will make macrophages from cord blood and adult blood and freeze them under many conditions: freezing solutions (including the one that already preserves tumor tissue), cell concentrations, freezing speeds and cell maturity. After thawing, we will count surviving cells and test whether they still eat pHGG cells in a standard tumor-eating (phagocytosis) test, with and without anti-CD47, compared with fresh cells from the same donor. 1.2 Ship and test in SLiCE. The best frozen cells will travel from Utah to UNC in liquid-nitrogen shipping containers with temperature monitors, then be thawed and added to brain slices carrying pHGG tissue. SLiCE will report tumor killing and any harm to normal brain tissue, and answer the key question: do cord-blood macrophages still outperform adult macrophages after freezing and shipping? The same frozen batch will also be tested in Utah as a cross-site check. Success = at least 70% of cells alive after thawing; at least 75% of fresh-cell tumor-eating activity; cord-blood advantage preserved; matching results at both sites. |  | Freeze, thaw and ship engineered macrophages that hunt NG2-positive tumor. 2.1 Find the recipe for engineered cells. Genetically engineered macrophages may be more fragile. We will repeat the freezing tests with NG2-targeted macrophages, checking after thawing that the cells are alive, still carry the NG2-targeting receptor, and still eat NG2-positive pHGG cells while sparing NG2-low cells. Non-engineered macrophages serve as controls. 2.2 Ship and test in SLiCE. Shipped NG2-targeted macrophages will be tested on pHGG tissue with high versus low NG2. SLiCE will show whether killing is selective for NG2-positive tumor and whether normal brain tissue is spared. Why it matters: NG2 levels vary from tumor to tumor. A ready-to-ship engineered cell lets SLiCE ask whether a particular child’s tumor has enough NG2 to respond, before any cell therapy is made for that child. Success = the same survival and activity targets, the receptor retained, and stronger killing of NG2-high than NG2-low tumor. |

# Rigor and risk management

| If this happens… | …we will |
| --- | --- |
| Macrophages are delicate and may not survive freezing. | Test many recipes in parallel. Back-up plan: freeze earlier-stage blood cells and finish maturing them after thawing at the hub. |
| Donors vary, patient tumors are scarce, and one lucky experiment could mislead us. | Every test uses at least three independent donors, fresh-cell and no-macrophage controls and repeat shipments, and is analyzed without knowing which condition is which. Frozen, quality-tested batches reduce donor swings, and banked frozen tumors let us schedule experiments instead of waiting for surgeries. |
| SLiCE uses rat brain tissue. | It reveals collateral damage to normal brain, but not every human-specific safety issue. Human-cell safety testing is planned for follow-on work. |

# 12-month timeline and milestones

| Activity (month →) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Set-up: SLiCE macrophage tracking; dry run with fresh cells (UNC) |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 Freeze, thaw and test cord-blood and adult macrophages (Utah) |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 Ship to UNC; SLiCE tests on pHGG tissue (Utah → UNC) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 Build, freeze, thaw and test NG2-targeted macrophages (Utah) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 Ship NG2-targeted cells; SLiCE tests, NG2-high vs. low (Utah → UNC) |  |  |  |  |  |  |  |  |  |  |  |  |
| Wrap-up: cross-site checks, protocol, manuscript, network plan (both) |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestones |  |  |  |  | M1 |  |  | M2 |  |  |  | M3 |

|  | Cheshier lab (Utah) |  | Satterlee lab (UNC) |  | Joint: ship, thaw and test in SLiCE |
| --- | --- | --- | --- | --- | --- |

| M1 · MONTH 5 Recipes validated. Freezing recipes work for cord-blood and adult macrophages. |  | M2 · MONTH 8 Travel proven. Shipped normal macrophages work in SLiCE; NG2-targeted freezing recipe in hand. |  | M3 · MONTH 12 Network-ready. Shipped NG2-targeted macrophages work in SLiCE; shipping protocol and report delivered. |
| --- | --- | --- | --- | --- |

# Impact and what comes next

Picture a surgeon at any partner hospital freezing a piece of a child’s tumor before leaving the operating room. Within days, a report arrives: which immunotherapies destroyed this tumor, and which spared the healthy brain. In 12 months, this project builds the missing link to that future:

- A shippable macrophage kit: validated freezing recipes for cord-blood, adult and NG2-targeted macrophages.

- Proof of travel: frozen immune cells that crossed institutions and worked in SLiCE.

- A blueprint: a step-by-step protocol any partner lab can follow, and the foundation for a multi-center network.

The same know-how can then extend to patient-matched immune cells, T cells, and other childhood brain tumors (medulloblastoma, DIPG and others also carry the CD47 signal3), positioning our team for multi-year, multi-center funding.

Children with brain tumors cannot wait for slow, uncertain testing. Test before you treat.

# Team and budget

| Utah · Dr. Samuel Cheshier |  | UNC · Dr. Andrew Satterlee |  | Budget · $75,000 over 12 months |
| --- | --- | --- | --- | --- |
| Pediatric neurosurgery and macrophage immunotherapy for brain tumors: the anti-CD47 studies,3 the cord-blood findings4 and NG2-targeted macrophages (with Dr. Minna Roh-Johnson’s laboratory).5,6 Leads: cell production, freezing and shipping. |  | Developer of SLiCE, which keeps patient tumors alive on living brain slices for four-day treatment testing, including with immune T cells.1,2 Leads: receiving shipments, SLiCE testing and the normal-brain safety readout. |  | $50,000 to Dr. Cheshier’s laboratory for cell production, freezing, engineering and shipping. $25,000 to Dr. Satterlee’s laboratory for SLiCE testing. Line items are in the separate budget document. |

REFERENCES

1.  Mann B, et al. A living ex vivo platform for functional, personalized brain cancer diagnosis. Cell Rep Med 2023;4:101042.

2.  Artz NM, et al. An ex vivo functional biomarker of treatment response in pediatric low-grade glioma. PLoS One 2026;21(3):e0331423.

3.  Gholamin S, Mitra SS, Feroze AH, et al. Disrupting the CD47-SIRPα anti-phagocytic axis by a humanized anti-CD47 antibody is an efficacious treatment for malignant pediatric brain tumors. Sci Transl Med 2017;9:eaaf2968.

4.  Baker C, Cooper A, Youssef OA, et al. Age-dependent changes in phagocytic efficiency by macrophages incubated with grade 3 pediatric medulloblastoma cells in response to anti-CD47 treatment. Manuscript in preparation.

5.  Kurudza E, Varady SRS, Greiner D, et al. NG2-targeting macrophages inhibit 3D invasion of patient-derived glioblastoma spheroids. bioRxiv 2026; doi:10.64898/2026.04.03.715398.

6.  Greiner D, Xue Q, Waddell TQA, et al. Human CSPG4-targeting CAR-macrophages inhibit melanoma growth. Oncogene 2025;44:1665–1677.